## Timeline
Week | Title | Difficulty level | Description | Due Date | Status | Comments
1 | Project Setup and Foundation | Medium | Initialize project structure (React + Vite frontend, Express + TypeScript backend), setup MongoDB Atlas database connection, implement basic authentication system (JWT, bcrypt), user registration and login endpoints, health check endpoint (/health), and initial project documentation (wireframes, database schema, data flow diagrams). | Week 1 | In Progress | Establish core foundation and development environment.
2 | Core Features Development | Medium | Implement user profile management (create/update profiles with bio, skills, experience, location), project posting functionality for clients (title, description, category, budget, requirements), freelancer search and filtering system, and basic proposal submission system (cover letter, proposed budget, timeline). | Week 2 | Planned | Focus on main functionality
3 | Communication and Project Management | Hard | Build proposal management system (accept/reject proposals, status tracking), implement real-time messaging system between users, file upload functionality (Multer integration for resumes and portfolio files), and project dashboard for freelancers and clients to view ongoing projects. | week3 | Planned | Complex real-time features
4 | Payment and Review Systems | Hard | Implement time tracking system (start/stop timer, duration calculation, time entry history), integrate Stripe Payment API (Payment Intents, secure card processing), build review and rating system (client-to-freelancer and freelancer-to-client reviews), and create admin dashboard (user management, project oversight, suspend/activate accounts). | week4 | Planned | Critical payment integration and admin functionality.
5 | Advanced Features and Testing | Medium | Develop notification system (real-time updates, read/unread status), enhance search functionality (advanced filtering by category, budget, skills, location, pagination), conduct comprehensive testing (unit tests, integration tests, usability testing), and implement UI/UX improvements (responsive design, loading states, error handling). | week5 | Planned | Polish features and ensure quality through testing.
6 | Optimization and Deployment | Medium | Performance optimization (database query optimization, API response caching, code splitting), final testing and bug fixes, complete technical documentation (API documentation, deployment guides), and deployment setup (Vercel for frontend, Render for backend, MongoDB Atlas configuration). | Week6 | Planned | Prepare for production deployment.
7 | Final Polish and Presentation | Easy | Final refinements (UI polish, accessibility improvements), user acceptance testing (UAT) with stakeholders, live deployment and monitoring, and presentation preparation (demo preparation, project documentation, presentation slides). | Week7 | Planned | Complete project and prepare for final presentation.
Note on B1: SWD: What is the component you are working on?
Note on C1: SWD: What is your perception of how difficult this component will be? Easy ¦ Medium ¦ Difficult
Note on D1: SWD: A brief description of the tasks for this component.
Note on E1: SWD: Your target date for completion
Note on F1: SWD: Not Started In Progress Stalled Completed
Note on G1: SWD: Notes or reminders concerning this component.